## RMS
| Screen/Function | Feature | Role | Level | LOC | Planned-In | In Charge (BE) | Done-In | RDS | Status | Updated | Update Details | Effort
| Authentication | Authorization and Authentication
1 | Sign in (web) |  | Tất cả | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 1 |  | Done | Done | Cập nhật deviceId vào request truyền về backend để kiểm soát thiết bị đăng nhập quen hay lạ | 2
2 | Sign in (mobile) |  | Tất cả | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done | Done | Cập nhật deviceId vào request truyền về backend để kiểm soát thiết bị đăng nhập quen hay lạ | 2
3 | Change password (web) |  | Tất cả | Simple | 60 | Iteration 1 | Dương Minh Hiếu | Iteration 1 |  | Done |  |  | 2
4 | Change password (mobile) |  | Tất cả | Simple | 60 | Iteration 4 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
5 | Forgot password (web) |  | Tất cả | Simple | 60 | Iteration 1 | Dương Minh Hiếu | Iteration 1 |  | Done |  |  | 2
6 | Forgot password (mobile) |  | Tất cả | Simple | 60 | Iteration 4 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
7 | Control login from unfamiliar devices |  | Tất cả | Medium | 120 | Iteration 1 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 4
8 | View profile |  | Tất cả | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 1 |  | Done |  |  | 2
9 | Update profile |  | Tất cả | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 1 |  | Done |  |  | 2
10 | System logging |  | Admin (phòng IT) | Medium | 120 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 4
Authorization (web)
11 | View website pages |  | Admin (phòng IT) | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 1 |  | Done |  |  | 2
12 | Activate/Inactivate website pages |  | Admin (phòng IT) | Medium | 120 | Iteration 1 | Trần Xuân Hoàn | Iteration 1 |  | Done |  |  | 4
13 | View access rights of employees |  | Admin (phòng IT) | Medium | 120 | Iteration 1 | Trần Xuân Hoàn | Iteration 1 |  | Done |  |  | 4
14 | Update access rights of employees |  | Admin (phòng IT) | Medium | 120 | Iteration 1 | Trần Xuân Hoàn | Iteration 1 |  | Done |  |  | 4
| Materials and equipments management | Device Management (web)
Roadmap
15 | View roadmaps list |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Dương Minh Hiếu | Iteration 2 |  | Done |  |  | 2
16 | Update roadmap |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 4
17 | Delete roadmap |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 4
18 | Create roadmap |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 2
Lateral
19 | View laterals list |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Dương Minh Hiếu | Iteration 2 |  | Done |  |  | 2
20 | Update lateral |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done | Done | Thêm cơ chế bắn sự kiện cho notification để tạo thông báo cho các phòng ban | 4
21 | Delete lateral |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done | Done | Thêm cơ chế bắn sự kiện cho notification để tạo thông báo cho các phòng ban | 4
22 | Create lateral |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 2
Commune
23 | View communes list |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Dương Minh Hiếu | Iteration 2 |  | Done |  |  | 2
24 | Update commune |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done | Done | Thêm cơ chế bắn sự kiện cho notification để tạo thông báo cho các phòng ban | 4
25 | Delete commune |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done | Done | Thêm cơ chế bắn sự kiện cho notification để tạo thông báo cho các phòng ban | 4
26 | Create commune |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 2
NeighborhoodUnit
27 | View neighborhood units list |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Dương Minh Hiếu | Iteration 2 |  | Done |  |  | 2
28 | Update neighborhood unit |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done | Done | Thêm cơ chế bắn sự kiện cho notification để tạo thông báo cho các phòng ban | 4
29 | Delete neighborhood unit |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done | Done | Thêm cơ chế bắn sự kiện cho notification để tạo thông báo cho các phòng ban | 4
30 | Create neighborhood unit |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 2
Road
31 | View roads list |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Dương Minh Hiếu | Iteration 2 |  | Done |  |  | 2
32 | Update road |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done | Done | Thêm cơ chế bắn sự kiện cho notification để tạo thông báo cho các phòng ban | 4
33 | Delete road |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done | Done | Thêm cơ chế bắn sự kiện cho notification để tạo thông báo cho các phòng ban | 4
34 | Create road |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 2
Hamlet
35 | View hamlets list |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Dương Minh Hiếu | Iteration 2 |  | Done |  |  | 2
36 | Update hamlet |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 4
37 | Delete hamlet |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 4
38 | Create hamlet |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 2
MaterialsPrice
39 | View materials prices list |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Dương Minh Hiếu | Iteration 2 |  | Done |  |  | 2
40 | Update materials price |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 4
41 | Delete materials price |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 4
42 | Create materials price |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 2
WaterMeterType
43 | View water meter types list |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
44 | Update water meter type |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
45 | Delete water meter type |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
46 | Create water meter type |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
MaterialsGroup
47 | View materials groups list |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
48 | Update materials group |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
49 | Delete materials group |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
50 | Create materials group |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
Unit
51 | View units list |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 1 |  | Done |  |  | 2
52 | Update unit |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
53 | Delete unit |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
54 | Create unit |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
System Parameter Management
55 | View list of system parameters |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 2
56 | Update system parameters |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
Water Price Management
57 | View list of water prices |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 2 |  | Done |  |  | 2
58 | Create new water price |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
59 | Update water price |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
60 | Delete water price |  | Admin (phòng IT) | Medium | 120 | Iteration 2 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
History of Updating Information Management
61 | View history of updating information |  | Admin (phòng IT) | Medium | 120 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 4
| Department Management | Internal Company Human Resources Management (web)
62 | View list of departments |  | Admin (phòng IT) | Simple | 60 | Iteration 3 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
63 | Create department |  | Admin (phòng IT) | Simple | 60 | Iteration 3 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
64 | Update department |  | Admin (phòng IT) | Simple | 60 | Iteration 3 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
65 | Delete department |  | Admin (phòng IT) | Medium | 120 | Iteration 3 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
Water Supply Network Management
66 | View list of branches |  | Admin (phòng IT) | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 1 |  | Done |  |  | 2
67 | Create branch |  | Admin (phòng IT) | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 1 |  | Done |  |  | 2
68 | Update branch |  | Admin (phòng IT) | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
69 | Delete branch |  | Admin (phòng IT) | Medium | 120 | Iteration 4 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
Employees Management
70 | View list of employees |  | Admin (phòng IT) | Simple | 60 | Iteration 2 | Trần Xuân Hoàn | Iteration 1 |  | Done |  |  | 2
71 | Create employee |  | Admin (phòng IT) | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 1 |  | Done |  |  | 2
72 | Update employee |  | Admin (phòng IT) | Simple | 60 | Iteration 3 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
73 | Delete employee |  | Admin (phòng IT) | Medium | 120 | Iteration 3 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 4
74 | Lock/Unlock account |  | Admin (phòng IT) | Medium | 120 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 4
Job Management
75 | View list of jobs |  | Admin (phòng IT) | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
76 | Create new job |  | Admin (phòng IT) | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
77 | Update job’s information |  | Admin (phòng IT) | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
78 | Delete job |  | Admin (phòng IT) | Medium | 120 | Iteration 4 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
| Manage new installation requests | Water Meter Lifecycle Management (web)
Installation requests
79 | View new installation requests list |  | Admin (phòng IT), Trưởng phòng KH-KT, Nhân viên nhận đơn KH-KT | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 1 |  | Done |  |  | 2
80 | Create new installation request |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT | Medium | 120 | Iteration 3 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
81 | Approve / reject installation requests |  | Admin (phòng IT), Nhân viên khảo sát KH-KT | Simple | 60 | Iteration 3 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
Receipt
82 | View receipts list |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT, Nhân viên tài vụ | Simple | 60 | Iteration 4 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
83 | Create receipt |  | Admin (phòng IT), Nhân viên tài vụ | Medium | 120 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 4
84 | Update receipt |  | Admin (phòng IT), Nhân viên tài vụ | Medium | 120 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 4
85 | Delete receipt |  | Admin (phòng IT), Nhân viên tài vụ | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
Requests solving
86 | Assign requests for processing |  | Admin (phòng IT), Trưởng phòng KH-KT, Trưởng chi nhánh thi công | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
87 | Create construction pending request |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
88 | Update construction pending request |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
Manage cost estimates
89 | View cost estimates list |  | Admin (phòng IT), Nhân viên khảo sát KH-KT, Trưởng phòng KH-KT, Lãnh đạo | Simple | 60 | Iteration 3 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
90 | Create new estimation |  | Admin (phòng IT), Nhân viên khảo sát KH-KT | Medium | 120 | Iteration 1 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
91 | Update estimation |  | Admin (phòng IT), Nhân viên khảo sát KH-KT | Medium | 120 | Iteration 1 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
92 | Approve / reject cost estimates |  | Admin (phòng IT), Trưởng phòng KH-KT | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
Contract management
93 | View contracts list |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT | Simple | 60 | Iteration 3 | Dương Minh Hiếu | Iteration 3 |  | Done |  |  | 2
94 | Create new contract |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT | Medium | 120 | Iteration 1 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 4
95 | Delete contract |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT | Medium | 120 | Iteration 1 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 4
Manage construction requests
96 | View pending construction request |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT, Trưởng chi nhánh thi công | Simple | 60 | Iteration 3 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
97 | Accept construction |  | Admin (phòng IT), Nhân viên khảo sát KH-KT | Simple | 60 | Iteration 1 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
Manage settlements
98 | View settlements list |  | Admin (phòng IT), Trưởng chi nhánh thi công, Nhân viên chi nhánh thi công, Lãnh đạo | Simple | 60 | Iteration 3 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
99 | Create new settlement |  | Admin (phòng IT), Nhân viên chi nhánh thi công | Medium | 120 | Iteration 1 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 4
100 | Update settlement |  | Admin (phòng IT), Nhân viên chi nhánh thi công | Simple | 60 | Iteration 1 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
Other
101 | Sign for confirmation |  | Admin (phòng IT), Trưởng chi nhánh thi công, Trưởng phòng KH-KT, Nhân viên khảo sát KH-KT, Lãnh đạo | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
102 | View reports and statistics of requests pending cost estimates | Report and Statistics Management (web) | Admin (phòng IT), Lãnh đạo | Complex | 240 | Iteration 3 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 6
103 | View reports and statistics of pending estimate approval requests |  | Admin (phòng IT), Lãnh đạo | Complex | 240 | Iteration 3 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 6
104 | View reports and statistics of estimation approval–rejected requests |  | Admin (phòng IT), Lãnh đạo | Complex | 240 | Iteration 3 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 6
105 | View reports and statistics of assigned survey |  | Admin (phòng IT), Lãnh đạo | Complex | 240 | Iteration 3 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 6
106 | View customers list | Customers Management (web) | Admin (phòng IT), Nhân viên nhận đơn KH-KT, Nhân viên khảo sát KH-KT, Trưởng phòng KH-KT | Simple | 60 | Iteration 3 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
107 | View customer details |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT, Nhân viên khảo sát KH-KT, Trưởng phòng KH-KT, Nhân viên chi nhánh thi công | Simple | 60 | Iteration 1 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
108 | Update customers information |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
109 | View customer' s water usage history |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT, Nhân viên ghi thu, Nhân viên khảo sát KH-KT | Simple | 60 | Iteration 4 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
110 | Delete customer |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT | Medium | 120 | Iteration 4 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 4
111 | Create customer |  | Admin (phòng IT), Nhân viên nhận đơn KH-KT | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 3 |  | Done |  |  | 2
112 | Get notifications (web) | System Portal Management | Trưởng phòng KH-KT, Admin (phòng IT), Nhân viên nhận đơn KH-KT, Nhân viên khảo sát KH-KT, Nhân viên tài vụ, Trưởng phòng Kinh doanh, Trưởng chi nhánh thi công, Lãnh đạo, Nhân viên chi nhánh thi công | Simple | 60 | Iteration 3 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
113 | Get notification (mobile) |  | Admin (phòng IT), Nhân viên ghi thu | Medium | 120 | Iteration 3 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 4
114 | Create notification |  | Admin (phòng IT) | Medium | 120 | Iteration 3 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 4
| Manage water meter recording | Meter Recording & Billing Workflow Management
115 | Capture water meter (mobile) |  | Admin (phòng IT), Nhân viên ghi thu | Medium | 120 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 4
Record this month’s meter readings
116 | Verify and validate meter readings (mobile) |  | Admin (phòng IT), Nhân viên ghi thu | Medium | 120 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 4
117 | View customers list of a roadmap (mobile) |  | Admin (phòng IT), Nhân viên ghi thu | Simple | 60 | Iteration 4 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
118 | View customer's information in the meter recording period (mobile) |  | Admin (phòng IT), Nhân viên ghi thu | Medium | 120 | Iteration 3 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 4
119 | View payment information list (mobile) |  | Admin (phòng IT), Nhân viên ghi thu | Simple | 60 | Iteration 4 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
120 | Update index (mobile) |  | Admin (phòng IT), Nhân viên ghi thu | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
Arrange meter recording roadmap (web)
121 | Assign meter recording roadmap |  | Admin (phòng IT), Trưởng phòng Kinh doanh | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
122 | Cancel meter recording roadmap assignments |  | Admin (phòng IT), Trưởng phòng Kinh doanh | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
123 | Update meter recording roadmap assignments |  | Admin (phòng IT), Trưởng phòng Kinh doanh | Simple | 60 | Iteration 4 | Trần Xuân Hoàn | Iteration 4 |  | Done |  |  | 2
124 | View assigned roadmap |  | Admin (phòng IT), Nhân viên ghi thu | Simple | 60 | Iteration 4 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
Bills Management (mobile)
125 | View water consumption volume |  | Admin (phòng IT) | Simple | 60 | Iteration 4 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
126 | View bill |  | Admin (phòng IT), Nhân viên ghi thu | Simple | 60 | Iteration 4 | Dương Minh Hiếu | Iteration 4 |  | Done |  |  | 2
[6 empty] | Total loc: | 10980 | [7 empty] | 26 | 47 | 21 |  | 94
[6 empty] | Iteration 1 | 2100 | [5 empty] | Teammates | Total Efforts | Iter1 | Iter2 | Iter3 | Iter4
[6 empty] | Iteration 2 | 4020 | [5 empty] | Trần Xuân Hoàn | 90 | 18 | 38 | 11 | 23
[6 empty] | Iteration 3 | 2340 | [5 empty] | Nguyễn Đức Dũng | 0 | 0 | 0 | 0 | 0
[6 empty] | Iteration 4 | 2520 | [5 empty] | Dương Minh Hiếu | 36 | 8 | 9 | 10 | 9
[13 empty] | Phạm Hải Đăng | 0 | 0 | 0 | 0 | 0
[13 empty] | Est.Effort | 358
[13 empty] | Use Cases | Done | Doing | Pending | Complete
[14 empty] | 126 | 0 | 0 | 0
[13 empty] | Tiến độ | 100.00%
[13 empty] | Còn lại | 0 use cases

## Iter1
No | Screen/Function | Description | Level | Loc | In Charge | RDS | Progress | Plan |  | Actual |  | Status
[8 empty] | Plan Start Date | Plan to Done | Actual Start | Actual Done
1 | Sign in (web) | Allow employees to log in using either their username or email, as long as the account exists and is activated. Both the username and password fields must be filled in. Authentication is handled via Keycloak. Allows a NAWACO employee to authenticate their identity using their username and password to access the system. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-01-19 | 2026-01-19 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-01-10 | 2026-01-10 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-01-19 | 2026-01-19 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-01-20 | 2026-01-20 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-10 | 2026-01-15 | 2026-01-20 | 2026-01-20 | Done
2 | Change password (web) | Allow users to change their password when necessary. To perform this action, the account must be activated, the user must already be logged in, and the password can only be changed from their own profile page. The new password must not be the same as the old one and must satisfy other business requirements. After confirming the password change, a notification email must be sent to the user’s registered email address, and a system notification (via the notification bell) should be triggered if the change is made from an unfamiliar device. Allows a user to update their account password for security reasons while they are already signed into the NAWACO system. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-01-19 | 2026-01-20 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-01-10 | 2026-01-15 | 2026-02-12 | 2026-02-12 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-01-19 | 2026-01-20 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-01-10 | 2026-01-15 | 2026-02-12 | 2026-02-12 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-10 | 2026-01-15 | 2026-01-20 | 2026-01-20 | Done
3 | Forgot password (web) | Allow users to reset their password if they forget it. The flow is as follows: From the login page, the user navigates to the “Forgot Password” page The user enters their registered email or username The system verifies the account; if valid, it generates and sends an OTP to the user’s email The user enters the OTP for verification The user sets a new password; after successful confirmation, a confirmation email must be sent Note: The OTP must have a limit on the number of incorrect attempts. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-01-19 | 2026-01-20 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-01-10 | 2026-01-15 | 2026-02-12 | 2026-02-12 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-01-19 | 2026-01-20 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-01-10 | 2026-01-15 | 2026-02-12 | 2026-02-12 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-10 | 2026-01-15 | 2026-01-20 | 2026-01-20 | Done
4 | Control login from unfamiliar devices | Enhance user security by monitoring logins from unfamiliar devices. When a new device is detected, the system still allows access but must send a confirmation email to the user and trigger a notification via the system’s notification bell. If the user confirms the device, the session continues and the device’s IP address is recorded as trusted. If the user indicates that the login attempt was not made by them, the system must immediately terminate the session on the unfamiliar device and guide the user to change their password. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-31 | 2026-03-31 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-01-21 | 2026-01-25 | 2026-03-30 | 2026-03-30 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-31 | 2026-03-31 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-01-21 | 2026-01-25 | 2026-03-30 | 2026-03-30 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-21 | 2026-01-25 | 2026-03-31 | 2026-03-31 | Done
5 | View profile | Allow users to view their profile information, including avatar, phone number, address, email, username, and other relevant details. Users can only access this information after successfully logging into the system. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-01-19 | 2026-01-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-01-11 | 2026-01-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-01-19 | 2026-01-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-03-03 | 2026-03-03 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-10 | 2026-01-15 | 2026-03-03 | 2026-03-03 | Done
6 | Update profile | Allow users to update their personal information. This page is only accessible after the user has successfully logged into the system. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-02-01 | 2026-02-21 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-01-11 | 2026-01-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-02-01 | 2026-02-21 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-03-03 | 2026-03-03 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-10 | 2026-01-15 | 2026-03-03 | 2026-03-03 | Done
7 | View website pages | Provide a page that allows the admin to view all websites deployed on the system, including both activated and deactivated sites. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-01-13 | 2026-01-14 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-01-12 | 2026-01-12 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-01-12 | 2026-01-14 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-03-03 | 2026-03-03 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-10 | 2026-01-15 | 2026-03-03 | 2026-03-03 | Done
8 | Activate/Inactivate website pages | Allow the admin to activate or hide a deployed website on the system. When a site is hidden, authorized employees will receive a notification, and the site will only be disabled after 10 minutes, giving them time to save their work. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-03-21 | 2026-03-21 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-03-03 | 2026-03-03 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-10 | 2026-01-15 | 2026-03-03 | 2026-03-03 | Done
9 | View access rights of employees | Allow the admin to assign access permissions to specific business web pages for each employee. Each employee is granted access to a limited number of pages based on their role and responsibilities. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-03-21 | 2026-03-21 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-03-03 | 2026-03-03 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-10 | 2026-01-15 | 2026-03-03 | 2026-03-03 | Done
10 | Update access rights of employees | Allow the admin to update employees’ access permissions to business web pages. When access is revoked, the employee will receive a notification and must save all ongoing work within 10 minutes before being completely denied access. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-03-03 | 2026-03-03 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-10 | 2026-01-15 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-10 | 2026-01-15 | 2026-03-03 | 2026-03-03 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-10 | 2026-01-15 | 2026-03-05 | 2026-03-06 | Done
11 | View list of branches | Allow users to view the list of water supply branches currently deployed in the system. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-05 | 2026-03-06 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-03 | 2026-03-03 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-05 | 2026-03-06 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-05 | 2026-03-06 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-16 | 2026-01-21 | 2026-03-05 | 2026-03-06 | Done
12 | Create branch | Allow users to create a new branch. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-05 | 2026-03-06 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-03 | 2026-03-03 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-05 | 2026-03-06 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-03 | 2026-03-03 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-16 | 2026-01-21 | 2026-03-05 | 2026-03-06 | Done
13 | Create employee | Allow users to create a new employee. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-02-16 | 2026-02-17 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-02-15 | 2026-02-15 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-02-16 | 2026-02-17 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-03 | 2026-03-03 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-16 | 2026-01-21 | 2026-03-05 | 2026-03-06 | Done
14 | View new installation requests list | Allow users to view new installation requests. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-05 | 2026-03-07 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-04 | 2026-03-06 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-05 | 2026-03-07 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-04 | 2026-03-06 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-16 | 2026-01-21 | 2026-03-05 | 2026-03-07 | Done
15 | Assign requests for processing | Allow the Head of the KH-KT Department to assign new installation requests to a specific survey staff member. The screen includes two tables: unassigned requests and assigned requests. Once the assignment is successful, the corresponding survey staff member will receive an immediate notification. For the Head of the Construction Branch, the screen displays a list of requests pending construction. Each record includes an option to assign a construction team leader to handle the request. After assignment, there must be an option to print the work order. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-14 | 2026-03-15 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-13 | 2026-03-14 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-14 | 2026-03-15 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-13 | 2026-03-14 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-16 | 2026-01-21 | 2026-03-14 | 2026-03-15 | Done
16 | Create construction pending request | Allow users to create a new pending construction request. This request includes the new installation request number, contract number, and other relevant details. After the request is created, the Business Branch will receive a notification. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-21 | 2026-03-22 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-20 | 2026-03-20 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-21 | 2026-03-22 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-20 | 2026-03-20 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-16 | 2026-01-21 | 2026-03-21 | 2026-03-22 | Done
17 | Update construction pending request | Allow users to update a pending construction request. The Construction Branch will receive a notification after the update is successfully completed. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-21 | 2026-03-22 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-20 | 2026-03-20 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-21 | 2026-03-22 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-20 | 2026-03-20 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-16 | 2026-01-21 | 2026-03-21 | 2026-03-22 | Done
18 | Create new estimation | Allow users to create a new estimate. The initial information of the estimate is automatically populated from the new installation request. Users will then define details such as unit prices of materials, the list of materials, and their quantities/specifications. After the estimate is created, the department manager will receive a corresponding notification. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-13 | 2026-03-15 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-12 | 2026-03-14 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-13 | 2026-03-15 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-12 | 2026-03-14 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-16 | 2026-01-21 | 2026-03-13 | 2026-03-15 | Done
19 | Update estimation | Allow users to update the information of an estimate. After the update is completed, the department manager will receive a notification. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-13 | 2026-03-15 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-12 | 2026-03-14 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-16 | 2026-01-21 | 2026-03-13 | 2026-03-15 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-16 | 2026-01-21 | 2026-03-12 | 2026-03-14 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-16 | 2026-01-21 | 2026-03-13 | 2026-03-15 | Done
20 | Approve / reject cost estimates | Allow users to approve or reject an estimate. If the estimate is rejected, the corresponding survey staff member will be notified. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-13 | 2026-03-15 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-13 | 2026-03-14 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-13 | 2026-03-15 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-13 | 2026-03-14 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-21 | 2026-01-25 | 2026-03-13 | 2026-03-15 | Done
21 | Create new contract | Allow users to create a new contract. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-20 | 2026-03-21 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-19 | 2026-03-19 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-20 | 2026-03-21 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-19 | 2026-03-19 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-21 | 2026-01-25 | 2026-03-20 | 2026-03-21 | Done
22 | Delete contract | Allow users to delete a contract. A contract can only be deleted if the customer cancels the use of the clean water service. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-20 | 2026-03-21 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-19 | 2026-03-19 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-20 | 2026-03-21 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-19 | 2026-03-19 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-21 | 2026-01-25 | 2026-03-20 | 2026-03-21 | Done
23 | Accept construction | Allow users to create and sign a construction acceptance report. This report can only be generated after the construction has been completed. The signatories include a representative from the KH-KT Department (survey staff) and the construction unit (construction team leader). | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-21 | 2026-03-21 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-21 | 2026-03-21 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
24 | Create new settlement | Allow users to create a new settlement. After the settlement is created, the department manager will receive a notification. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-01-21 | 2026-01-25 | 2026-03-18 | 2026-03-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-01-21 | 2026-01-25 | 2026-03-18 | 2026-03-18 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
25 | Update settlement | Allow users to update a settlement. After the update is completed, the department manager will receive a notification. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-01-21 | 2026-01-25 | 2026-03-19 | 2026-03-19 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-01-21 | 2026-01-25 | 2026-03-19 | 2026-03-19 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
26 | Sign for confirmation | Allow users to sign estimates and settlements. When the document owner submits a document for signatures: - They will receive a notification once the document has been fully signed. - The assigned signatories will also receive notifications requesting them to sign the document. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-20 | 2026-03-17 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-20 | 2026-03-17 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
27 | View customer details | Allow users to view customer information, including name, age, address, ID number (Citizen Identification), bank account number, the most recent water meter image, and other relevant details. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-01-21 | 2026-01-25 | 2026-03-15 | 2026-03-15 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-01-21 | 2026-01-25 | 2026-03-15 | 2026-03-15 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-21 | 2026-01-25 | 2026-03-22 | 2026-03-23 | Done
28 | Update branch |  | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-05 | 2026-03-06 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-04 | 2026-03-04 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-05 | 2026-03-06 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-04 | 2026-03-04 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-21 | 2026-01-25 | 2026-03-05 | 2026-03-06 | Done
29 | Delete branch |  | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-05 | 2026-03-06 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-04 | 2026-03-04 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-21 | 2026-01-25 | 2026-03-05 | 2026-03-06 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-21 | 2026-01-25 | 2026-03-04 | 2026-03-04 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-21 | 2026-01-25 | 2026-03-05 | 2026-03-06 | Done

## Iter2
No | Screen/Function | Description | Level | Loc | In Charge | RDS | Progress | Plan |  | Actual |  | Status
[8 empty] | Plan Start Date | Plan to Done | Actual Start | Actual Done
1 | View roadmaps list | Allow employees to view meter reading routes with full search and filtering capabilities. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
2 | Update roadmap | Allow the admin to update information of a meter reading route. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-19 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
3 | Delete roadmap | Allow the admin to delete a meter reading route. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-19 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
4 | Create roadmap | Allow employees to create a new meter reading route. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-19 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
5 | View laterals list | Allow the admin to view the list of main branches with full search and filtering capabilities. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
6 | Update lateral | Allow the admin to update main branch information. After the update, the system must notify all departments. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-19 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
7 | Delete lateral | Allow the admin to delete a main branch. After deletion, the system must notify all departments. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-19 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
8 | Create lateral | Allow the admin to create a new main branch. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-19 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-20 | 2026-02-21 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
9 | View communes list | Allow the admin to view the list of wards/communes with full search and filtering capabilities. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
10 | Update commune | Allow the admin to update ward/commune information. After the update, the system must notify all departments. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-18 | 2026-02-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
11 | Delete commune | Allow the admin to delete a ward/commune. After deletion, the system must notify all departments. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-18 | 2026-02-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
12 | Create commune | Allow the admin to create a new ward/commune. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-18 | 2026-02-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-26 | 2026-02-27 | Done
13 | View neighborhood units list | Allow the admin to view the list of residential groups/areas/streets with full search and filtering capabilities. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
14 | Update neighborhood unit | Allow the admin to update information of a residential group/area/street. After the update, the system must notify all departments. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-18 | 2026-02-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
15 | Delete neighborhood unit | Allow the admin to delete a residential group/area/street. After deletion, the system must notify all departments. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-18 | 2026-02-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
16 | Create neighborhood unit | Allow the admin to create a new ward/commune. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-18 | 2026-02-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
17 | View roads list | Allow the admin to view the list of streets with full search and filtering capabilities. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-21 | 2026-02-22 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-21 | 2026-02-22 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
18 | Update road | Allow the admin to update street information. After the update, the system must notify all departments. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-21 | 2026-02-22 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-19 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-21 | 2026-02-22 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
19 | Delete road | Allow the admin to delete a street. After deletion, the system must notify all departments. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-21 | 2026-02-22 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-19 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-21 | 2026-02-22 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
20 | Create road | Allow the admin to create a new street. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-21 | 2026-02-22 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-19 | 2026-02-19 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-01-26 | 2026-02-01 | 2026-02-21 | 2026-02-22 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-01-26 | 2026-02-01 | 2026-02-27 | 2026-02-28 | Done
21 | View hamlets list | Allow the admin to view the list of villages/hamlets with full search and filtering capabilities. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-21 | 2026-02-22 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-02-02 | 2026-02-08 | 2026-02-27 | 2026-02-28 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-21 | 2026-02-22 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-02-02 | 2026-02-08 | 2026-02-27 | 2026-02-28 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-02-27 | 2026-02-28 | Done
22 | Update hamlet | Allow the admin to update village/hamlet information. After the update, the system must notify all departments. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-21 | 2026-02-22 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-02-20 | 2026-02-20 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-21 | 2026-02-22 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-02-27 | 2026-02-28 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-02-27 | 2026-02-28 | Done
23 | Delete hamlet | Allow the admin to delete a village/hamlet. After deletion, the system must notify all departments. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-21 | 2026-02-22 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-02-20 | 2026-02-20 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-21 | 2026-02-22 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-02-27 | 2026-02-28 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-02-27 | 2026-02-28 | Done
24 | Create hamlet | Allow the admin to create a new village/hamlet. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-21 | 2026-02-22 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-02-20 | 2026-02-20 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-21 | 2026-02-22 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-02-27 | 2026-02-28 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-02-27 | 2026-02-28 | Done
25 | View materials prices list | Allow the admin to view the list of material unit prices with full search and filtering capabilities. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-04 | 2026-03-05 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-02-02 | 2026-02-08 | 2026-03-03 | 2026-03-03 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-04 | 2026-03-05 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-02-02 | 2026-02-08 | 2026-03-04 | 2026-03-05 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-04 | 2026-03-05 | Done
26 | Update materials price | Allow the admin to update material unit price information. After the update, the system must notify the KH-KT Department and the Construction Branch. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-26 | 2026-02-27 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-02-25 | 2026-02-25 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-26 | 2026-02-27 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-04 | 2026-03-05 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-04 | 2026-03-05 | Done
27 | Delete materials price | Allow the admin to delete a material unit price. After deletion, the system must notify the KH-KT Department and the Construction Branch. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-26 | 2026-02-27 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-02-25 | 2026-02-25 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-26 | 2026-02-27 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-04 | 2026-03-05 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-04 | 2026-03-05 | Done
28 | Create materials price | Allow the admin to create a new material unit price. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-26 | 2026-02-27 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-02-25 | 2026-02-25 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-26 | 2026-02-27 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-04 | 2026-03-05 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-04 | 2026-03-05 | Done
29 | View water meter types list | Allow the admin to view the list of water meter groups in the company with full search and filtering capabilities. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-06 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-02-02 | 2026-02-08 | 2026-03-18 | 2026-03-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-06 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-06 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-06 | Done
30 | Update water meter type | Allow the admin to update a water meter group. After the update, the system must notify the KH-KT Department and the Construction Branch. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-06 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-07 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-06 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-07 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-07 | Done
31 | Delete water meter type | Allow the admin to delete a water meter group. The group can only be deleted if it contains no water meters, and the system must notify the KH-KT Department and the Construction Branch. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-06 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-06 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-11 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
32 | Create water meter type | Allow the admin to create a new water meter type. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-06 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-06 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-11 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
33 | View materials groups list | Allow the admin to view the list of material groups such as “Coupling”, “Reducer”, “Elbow” with full search and filtering capabilities. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-11 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-02-02 | 2026-02-08 | 2026-03-10 | 2026-03-10 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-11 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
34 | Update materials group | Allow the admin to update a material group. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-11 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-08 | 2026-03-08 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-11 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
35 | Delete materials group | Allow the admin to delete a material group. The group can only be deleted if it contains no materials. After deletion, the system must notify the KH-KT Department and the Construction Branch. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-11 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-08 | 2026-03-08 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-11 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
36 | Create materials group | Allow the admin to create a new material group. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-11 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-08 | 2026-03-08 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-11 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
37 | View units list | Allow the admin to view the list of measurement units with full search and filtering capabilities. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-06 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-05 | 2026-03-06 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-13 | Done
38 | Update unit | Allow the admin to update a measurement unit. After the update, the system must notify the KH-KT Department, Construction Branch, and Business Department. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-12 | 2026-03-13 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-10 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-12 | 2026-03-13 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-12 | 2026-03-14 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-13 | 2026-03-15 | Done
39 | Delete unit | Allow the admin to delete a measurement unit. It must not be in use, and the system must notify the KH-KT Department, Construction Branch, and Business Department. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-12 | 2026-03-13 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-10 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-12 | 2026-03-13 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-12 | 2026-03-14 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-13 | 2026-03-15 | Done
40 | Create unit | Allow the admin to create a new measurement unit. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-12 | 2026-03-13 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-10 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-12 | 2026-03-13 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-12 | 2026-03-14 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-13 | 2026-03-15 | Done
41 | View list of system parameters | Allow the admin to view the list of system parameters with full search and filtering capabilities. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-15 | 2026-02-16 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-02-14 | 2026-02-14 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-02-15 | 2026-02-16 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-15 | 2026-03-17 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-16 | 2026-03-17 | Done
42 | Update system parameters | Allow the admin to update parameter information. After the update, the system must notify the KH-KT Department and the Construction Branch. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-12 | 2026-03-12 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-11 | 2026-03-12 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-02 | 2026-02-08 | 2026-03-12 | 2026-03-12 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-02 | 2026-02-08 | 2026-03-15 | 2026-03-17 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-02 | 2026-02-08 | 2026-03-16 | 2026-03-17 | Done
43 | View list of water prices | Allow users to view the list of water pricing. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-19 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-02-18 | 2026-02-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-19 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-19 | 2026-03-20 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-18 | 2026-03-21 | Done
44 | Create new water price | Allow users to create new water pricing. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-06 | 2026-03-06 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-05 | 2026-03-08 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-06 | 2026-03-06 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-15 | 2026-03-17 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-16 | 2026-03-17 | Done
45 | Update water price | Allow users to update water pricing. After the update, the system must notify the KH-KT Department, Construction Branch, and Business Department. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-06 | 2026-03-06 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-05 | 2026-03-08 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-06 | 2026-03-06 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-15 | 2026-03-17 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-16 | 2026-03-17 | Done
46 | Delete water price | Allow users to delete water pricing. It can only be deleted if not applied to any customer. After deletion, the system must notify the KH-KT Department, Construction Branch, and Business Department. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-06 | 2026-03-06 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-05 | 2026-03-08 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-06 | 2026-03-06 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-15 | 2026-03-17 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-16 | 2026-03-17 | Done
47 | View history of updating information | Allow the admin to view the edit history of all information in the Device Management module. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-22 | 2026-03-22 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-21 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-22 | 2026-03-22 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-22 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-22 | 2026-03-24 | Done
48 | View list of departments | Allow users to view the list of departments. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-02-18 | 2026-02-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-22 | 2026-03-22 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-21 | Done
49 | Create department | Allow users to create a new department. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-05 | 2026-03-05 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-22 | 2026-03-22 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-21 | Done
50 | Update department | Allow users to update department information. The updated department will receive a system notification. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-05 | 2026-03-05 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-22 | 2026-03-22 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-21 | Done
51 | Delete department | Allow users to delete a department. It must not contain any employees, and the system must notify other departments. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-02-16 | 2026-02-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-02-16 | 2026-02-18 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-02-20 | 2026-02-22 | Done
52 | Update branch | Allow users to update a branch. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-02-16 | 2026-02-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-02-16 | 2026-02-18 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-02-20 | 2026-02-22 | Done
53 | Delete branch | Allow users to delete a branch if it no longer contains any related information. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-02-16 | 2026-02-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-02-19 | 2026-02-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-02-16 | 2026-02-18 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-02-20 | 2026-02-22 | Done
54 | View list of employees | Allow users to view the list of employees. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-18 | 2026-03-19 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-02-11 | 2026-02-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-18 | 2026-03-19 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-17 | 2026-03-19 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-18 | 2026-03-20 | Done
55 | Update employee | Allow users to update an employee. The corresponding employee will receive a general notification (without detailed content) and be advised to check their profile for changes. Only IT staff can perform updates. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-18 | 2026-03-19 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-17 | 2026-03-17 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-18 | 2026-03-19 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-17 | 2026-03-19 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-18 | 2026-03-20 | Done
56 | Delete employee | Allow IT staff to delete an employee. Deletion is only allowed when no related data exists. Before permanent deletion, an email notification must be sent to the employee. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-18 | 2026-03-19 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-17 | 2026-03-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-18 | 2026-03-19 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-17 | 2026-03-19 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-18 | 2026-03-20 | Done
57 | View list of jobs | Allow users to view the list of tasks. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-12 | 2026-03-13 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-11 | 2026-03-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-12 | 2026-03-13 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-11 | 2026-03-12 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-12 | 2026-03-14 | Done
58 | Update job’s information | Allow users to update task information. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-12 | 2026-03-13 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-11 | 2026-03-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-12 | 2026-03-13 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-11 | 2026-03-12 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-12 | 2026-03-14 | Done
59 | Delete job | Allow users to delete a task if no employees are assigned to it. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-12 | 2026-03-13 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-11 | 2026-03-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-12 | 2026-03-13 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-11 | 2026-03-12 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-12 | 2026-03-14 | Done
60 | View receipts list | Allow users to view the list of payment receipts. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-22 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-02-09 | 2026-02-15 | 2026-03-20 | 2026-03-21 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-22 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-02-09 | 2026-02-15 | 2026-03-20 | 2026-03-22 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-23 | Done
61 | Create receipt | Allow users to create a new receipt. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-22 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-20 | 2026-03-21 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-22 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-20 | 2026-03-22 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-23 | Done
62 | Update receipt | Allow users to update a receipt. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-22 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-20 | 2026-03-21 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-22 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-20 | 2026-03-22 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-23 | Done
63 | Delete receipt | Allow users to delete a receipt. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-22 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-20 | 2026-03-21 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-22 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-09 | 2026-02-15 | 2026-03-20 | 2026-03-22 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-09 | 2026-02-15 | 2026-03-21 | 2026-03-23 | Done
docker run -d --name apps-auth-service-1 -p ghcr.io/tranhoan-backend-dev/capstone-project/auth:latest
docker run -d --name <container-name> -p <host-port>:<container-port> ghcr.io/tranhoan-backend-dev/capstone-project/organization:latest
docker run -d --name <container-name> -p <host-port>:<container-port> ghcr.io/tranhoan-backend-dev/capstone-project/device:latest
docker run -d --name <container-name> -p <host-port>:<container-port> ghcr.io/tranhoan-backend-dev/capstone-project/customer:latest
docker run -d --name <container-name> -p <host-port>:<container-port> ghcr.io/tranhoan-backend-dev/capstone-project/notification:latest
docker run -d --name <container-name> -p <host-port>:<container-port> ghcr.io/tranhoan-backend-dev/capstone-project/auth:latest
docker run -d --name <container-name> -p <host-port>:<container-port> ghcr.io/tranhoan-backend-dev/capstone-project/construction:latest
docker run -d --name <container-name> -p <host-port>:<container-port> ghcr.io/tranhoan-backend-dev/capstone-project/image:latest
docker run -d --name <container-name> -p <host-port>:<container-port> ghcr.io/tranhoan-backend-dev/capstone-project/gateway:latest
docker run -d --name <container-name> -p <host-port>:<container-port> ghcr.io/tranhoan-backend-dev/capstone-project/gateway:latest

## Iter3
| Screen/Function | Description | Level | Loc | In Charge | RDS | Progress | Plan |  | Actual |  | Status
[8 empty] | Plan Start Date | Plan to Done | Actual Start | Actual Done
1 | Create new installation request | Allow employees to receive and create new installation requests. After a request is successfully created, it will be immediately displayed in the department manager’s unassigned list, along with a notification sent to the manager’s account. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-23 | 2026-03-01 | 2026-03-06 | 2026-03-08 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-23 | 2026-03-01 | 2026-03-05 | 2026-03-06 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-23 | 2026-03-01 | 2026-03-06 | 2026-03-08 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-23 | 2026-03-01 | 2026-03-05 | 2026-03-06 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-23 | 2026-03-01 | 2026-03-09 | 2026-03-10 | Done
2 | Approve / reject installation requests | Allow users to approve new installation requests. This screen includes two sections: requests pending design, and processed requests awaiting connection or rejected designs. Users will approve a request if the information is valid, or reject it if there are issues. Approved requests will be directly embedded into future estimates. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-23 | 2026-03-01 | 2026-03-06 | 2026-03-08 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-23 | 2026-03-01 | 2026-03-05 | 2026-03-07 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-23 | 2026-03-01 | 2026-03-06 | 2026-03-08 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-23 | 2026-03-01 | 2026-03-05 | 2026-03-06 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-23 | 2026-03-01 | 2026-03-09 | 2026-03-10 | Done
3 | View cost estimates list | Allow users to view the list of estimates. The department manager can approve or reject estimates. When an estimate is approved or rejected, the corresponding survey staff member will receive a notification. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-23 | 2026-03-01 | 2026-03-07 | 2026-03-09 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-23 | 2026-03-01 | 2026-03-05 | 2026-03-06 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-23 | 2026-03-01 | 2026-03-07 | 2026-03-09 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-23 | 2026-03-01 | 2026-03-05 | 2026-03-06 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-23 | 2026-03-01 | 2026-03-09 | 2026-03-10 | Done
4 | View contracts list | Allow users to view the list of water supply contracts. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-23 | 2026-03-01 | 2026-03-13 | 2026-03-15 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-23 | 2026-03-01 | 2026-03-11 | 2026-03-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-23 | 2026-03-01 | 2026-03-13 | 2026-03-15 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-23 | 2026-03-01 | 2026-03-11 | 2026-03-11 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-23 | 2026-03-01 | 2026-03-14 | 2026-03-16 | Done
5 | View pending construction request | Allow users to view the list of pending construction requests. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-23 | 2026-03-01 | 2026-03-13 | 2026-03-15 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-23 | 2026-03-01 | 2026-03-11 | 2026-03-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-02-23 | 2026-03-01 | 2026-03-13 | 2026-03-15 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-02-23 | 2026-03-01 | 2026-03-11 | 2026-03-11 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-02-23 | 2026-03-01 | 2026-03-14 | 2026-03-16 | Done
6 | View settlements list | Allow users to view the list of settlements. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-02 | 2026-03-08 | 2026-03-13 | 2026-03-15 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-02 | 2026-03-08 | 2026-03-11 | 2026-03-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-02 | 2026-03-08 | 2026-03-13 | 2026-03-15 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-02 | 2026-03-08 | 2026-03-11 | 2026-03-11 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-02 | 2026-03-08 | 2026-03-14 | 2026-03-16 | Done
7 | View reports and statistics of requests pending cost estimates | Allow users to view reports and statistics on requests pending estimate creation. | Complex | 240
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-02 | 2026-03-08 | 2026-03-24 | 2026-03-28 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-02 | 2026-03-08 | 2026-03-27 | 2026-03-27 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-02 | 2026-03-08 | 2026-03-24 | 2026-03-28 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-03-02 | 2026-03-08 | 2026-03-27 | 2026-03-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-02 | 2026-03-08 | 2026-03-27 | 2026-03-29 | Done
8 | View reports and statistics of pending estimate approval requests | Allow users to view reports and statistics on estimates awaiting approval. | Complex | 240
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-02 | 2026-03-08 | 2026-03-24 | 2026-03-28 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-02 | 2026-03-08 | 2026-03-27 | 2026-03-27 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-02 | 2026-03-08 | 2026-03-24 | 2026-03-28 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-03-02 | 2026-03-08 | 2026-03-27 | 2026-03-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-02 | 2026-03-08 | 2026-03-27 | 2026-03-29 | Done
9 | View reports and statistics of estimation approval–rejected requests | Allow users to view reports and statistics on approved or rejected estimates. | Complex | 240
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-02 | 2026-03-08 | 2026-03-24 | 2026-03-28 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-02 | 2026-03-08 | 2026-03-27 | 2026-03-27 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-02 | 2026-03-08 | 2026-03-24 | 2026-03-28 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-03-02 | 2026-03-08 | 2026-03-27 | 2026-03-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-02 | 2026-03-08 | 2026-03-27 | 2026-03-29 | Done
10 | View reports and statistics of assigned survey | Allow users to view reports and statistics on requests assigned for survey. | Complex | 240
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-02 | 2026-03-08 | 2026-03-24 | 2026-03-28 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-02 | 2026-03-08 | 2026-03-27 | 2026-03-27 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-02 | 2026-03-08 | 2026-03-24 | 2026-03-28 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-03-02 | 2026-03-08 | 2026-03-27 | 2026-03-27 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-02 | 2026-03-08 | 2026-03-27 | 2026-03-29 | Done
11 | View customers list | Allow users to view the list of customers. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-08 | 2026-03-15 | 2026-03-21 | 2026-03-23 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-08 | 2026-03-15 | 2026-03-20 | 2026-03-20 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-08 | 2026-03-15 | 2026-03-21 | 2026-03-23 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-03-08 | 2026-03-15 | 2026-03-20 | 2026-03-21 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-24 | Done
12 | Create notification | Allow users to create notifications to send to employees in target departments. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-08 | 2026-03-15 | 2026-03-21 | 2026-03-23 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-08 | 2026-03-15 | 2026-03-20 | 2026-03-20 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-08 | 2026-03-15 | 2026-03-21 | 2026-03-23 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-08 | 2026-03-15 | 2026-03-20 | 2026-03-21 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-24 | Done
13 | View customer's information in the meter recording period |  | Medium | 120
| FE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-08 | 2026-03-15 | 2026-03-30 | 2026-04-01 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-23 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-08 | 2026-03-15 | 2026-03-30 | 2026-04-01 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-08 | 2026-03-15 | 2026-03-31 | 2026-04-03 | Done
14 | Get notification (web) | Allow users to retrieve the list of notifications. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-08 | 2026-03-15 | 2026-03-30 | 2026-04-01 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-23 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-08 | 2026-03-15 | 2026-03-30 | 2026-04-01 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-08 | 2026-03-15 | 2026-03-31 | 2026-04-03 | Done
15 | Get notification (mobile) | Allow users to retrieve the list of notifications on mobile devices. | Medium | 120
| FE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-08 | 2026-03-15 | 2026-03-30 | 2026-04-01 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-23 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-08 | 2026-03-15 | 2026-03-30 | 2026-04-01 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-08 | 2026-03-15 | 2026-03-31 | 2026-04-03 | Done

## Iter4
No | Screen/Function | Description | Level | Loc | In Charge | RDS | Progress | Plan |  | Actual |  | Status
[8 empty] | Plan Start Date | Plan to Done | Actual Start | Actual Done
1 | Sign in (mobile) | Allow employees to log in using either their username or email, as long as the account exists and is activated. Both username and password fields must be filled. Authentication is handled via Keycloak. | Simple | 60
| FE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-20 | 2026-03-21 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-20 | 2026-03-21 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-20 | 2026-03-21 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-20 | 2026-03-21 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-16 | 2026-03-22 | 2026-03-21 | 2026-03-22 | Done
2 | Change password (mobile) | Allow users to change their password when necessary. The account must be activated, the user must already be logged in, and the password can only be changed from their own profile page. The new password must not match the old one and must meet other business requirements. After confirmation, a notification email must be sent to the registered email address. | Simple | 60
| FE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-24 | Done
3 | Forgot password (mobile) | Allow users to reset their password if forgotten. The flow is as follows: From the login page, navigate to the “Forgot Password” page Enter registered email or username The system verifies the account and sends an OTP to the user’s email The user enters the OTP for verification The user sets a new password; upon success, a confirmation email is sent Note: The OTP must have a limit on incorrect attempts. | Simple | 60
| FE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-24 | Done
4 | System logging | Record all user activities, including login attempts, login devices, and changes to personal information and passwords. This page is accessible only to admins. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-24 | Done
5 | Lock/Unlock account | Allow users to lock or unlock user accounts. When locked, employees cannot log in. If they are currently logged in, they will receive a notification, and after 5 minutes their session will be terminated. A corresponding email notification must also be sent. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-16 | 2026-03-22 | 2026-03-22 | 2026-03-24 | Done
6 | Create new job | Allow users to create new tasks. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-12 | 2026-03-13 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-11 | 2026-03-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-12 | 2026-03-13 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-11 | 2026-03-11 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-16 | 2026-03-22 | 2026-03-12 | 2026-03-14 | Done
7 | Update customers information | Allow users to update customer information. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-19 | 2026-03-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-18 | 2026-03-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-19 | 2026-03-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-18 | 2026-03-18 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-16 | 2026-03-22 | 2026-03-19 | 2026-03-21 | Done
8 | View customer' s water usage history | Allow users to view a customer’s water usage history. Meter-reading staff can only view the most recent 3 months of consumption. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-19 | 2026-03-20 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-18 | 2026-03-18 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-19 | 2026-03-20 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-18 | 2026-03-18 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-16 | 2026-03-22 | 2026-03-19 | 2026-03-21 | Done
9 | Delete customer | Allow users to delete a customer. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-12 | 2026-03-13 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-11 | 2026-03-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-12 | 2026-03-13 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-11 | 2026-03-11 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-16 | 2026-03-22 | 2026-03-12 | 2026-03-14 | Done
10 | Create customer | Allow users to create a new customer. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-12 | 2026-03-13 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-11 | 2026-03-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-16 | 2026-03-22 | 2026-03-12 | 2026-03-13 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-16 | 2026-03-22 | 2026-03-11 | 2026-03-11 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-16 | 2026-03-22 | 2026-03-12 | 2026-03-14 | Done
11 | Capture water meter (mobile) | Allow users to capture water meter images. The meter must be clearly visible, including serial number and reading. After capture, the system stores the image and sends it to AI to extract the serial number and reading. Only one meter image per month is allowed to be recorded. | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-03-12 | 2026-03-13 | Done
| BE |  |  |  | Phạm Hải Đăng |  |  | 2026-03-23 | 2026-03-29 | 2026-03-11 | 2026-03-11 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-03-12 | 2026-03-13 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-23 | 2026-03-29 | 2026-03-11 | 2026-03-11 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-23 | 2026-03-29 | 2026-03-12 | 2026-03-14 | Done
12 | Verify and validate meter readings (mobile) | Allow users to verify water meter readings after capturing images. The process includes: Capture image Before saving, the system checks image quality; if unclear, require retake or manual input If valid, send an asynchronous event to AI for processing At the end of the day, the system aggregates all images and AI results (serial number and reading) The system displays each image with extracted data for user verification; if correct, approve and store in DB; otherwise, manually adjust | Medium | 120
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-08 | Done
| BE |  |  |  | Phạm Hải Đăng |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-03-07 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-08 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-23 | 2026-03-29 | 2026-03-23 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-09 | Done
13 | View customers list of a roadmap | Allow users to view the list of customers within a meter reading route. | Simple | 60
| FE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-23 | 2026-03-29 | 2026-03-29 | 2026-03-30 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-23 | 2026-03-29 | 2026-03-29 | 2026-03-30 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-03-29 | 2026-03-30 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-03-23 | 2026-03-29 | 2026-03-29 | 2026-03-30 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-23 | 2026-03-29 | 2026-03-30 | 2026-03-31 | Done
14 | View payment information list (mobile) | Allow users to view customer payment information, including bank transfer or cash. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-24 | Done
15 | Update index (mobile) | Allow users to manually update meter readings in case of errors. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-24 | Done
16 | Assign meter recording roadmap | Allow users to view meter reading routes and assign meter-reading staff to specific routes. Upon assignment, the staff will receive a notification. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-24 | Done
17 | Cancel meter recording roadmap assignments | Allow users to cancel route assignments. The assigned staff will receive a notification. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-23 | 2026-03-29 | 2026-03-22 | 2026-03-24 | Done
18 | Update meter recording roadmap assignments | Allow users to update route assignments. When reassigned, both previous and new staff will receive notifications. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-08 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-03-07 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-08 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-23 | 2026-03-29 | 2026-03-23 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-09 | Done
19 | View assigned roadmap | Allow users to view the routes assigned to them for meter reading. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-08 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-03-07 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-08 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-03-23 | 2026-03-29 | 2026-03-23 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-09 | Done
20 | View water consumption volume | Allow users to view water consumption for each customer, primarily for monitoring, validation, and anomaly detection. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-08 | Done
| BE |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-03-07 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-08 | Done
| SDS |  |  |  | Trần Xuân Hoàn |  |  | 2026-03-23 | 2026-03-29 | 2026-03-23 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-09 | Done
21 | View bill | Allow users to view the current month’s water bill for a customer. | Simple | 60
| FE |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-08 | Done
| BE |  |  |  | Dương Minh Hiếu |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-03-07 | Done
| SRS |  |  |  | Nguyễn Đức Dũng |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-08 | Done
| SDS |  |  |  | Dương Minh Hiếu |  |  | 2026-03-23 | 2026-03-29 | 2026-03-23 | 2026-03-23 | Done
| Test |  |  |  | Phạm Trường Giang |  |  | 2026-03-23 | 2026-03-29 | 2026-04-07 | 2026-04-09 | Done