## W1
PROJECT REPORT
Group | SEP490_G39
Week | 05/01/2026-11/01/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 1 Project Introduction, Report 2: Project Management Plan | HoanTX | Completed | Overview Project, Existing Solutions, Overview Project Management Plan, Responsibility Assignments
2 | Report 1 Project Introduction, Report 2: Project Management Plan | DungND | Completed | Product Background, Project Communications, Configuration Management
3 | Report 1 Project Introduction, Report 2: Project Management Plan | DangPH | Completed | Solution & Opportunity
4 | Report 1 Project Introduction, Report 2: Project Management Plan | GiangPT | Completed | Project Scope & Limitations, Quality Management
5 | Report 1 Project Introduction, Report 2: Project Management Plan | HieuDM | Completed | Management Approach, Project Training Plan
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 3: SRS v1.0 (Overall Requirement) | HoanTX | 2026-01-11 | Entity Relationship Diagram, Business Rules
2 | Report 3: SRS v1.0 (Overall Requirement) | DungND | 2026-01-11 | Main Workflows, Actors, Context Diagram, System Messages
3 | Report 3: SRS v1.0 (Overall Requirement) | DangPH | 2026-01-11 | Non-UI Functions, Non-Functional Requirements
4 | Report 3: SRS v1.0 (Overall Requirement) | GiangPT | 2026-01-11 | Use Cases
5 | Report 3: SRS v1.0 (Overall Requirement) | HieuDM | 2026-01-11 | Use Cases
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W2
PROJECT REPORT
Group | SEP490_G39
Week | 12/01/2026-18/01/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 1, 2, 3 | HoanTX | Completed | Entity Relationship Diagram, Business Rules
2 | Report 1, 2, 3 | DungND | Completed | Main Workflows, Actors, Context Diagram, System Messages
3 | Report 1, 2, 3 | DangPH | Completed | Non-UI Functions, Non-Functional Requirements
4 | Report 1, 2, 3 | GiangPT | Completed | Update Major Features (rp1), update Project Risks + Defect Rate (rp2)
5 | Report 1, 2, 3 | HieuDM | Completed | Use Cases, responsibility assignment, design mockup
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Incorrect definition of risk | GiangPT | Completed | Risk is different from issue (problem) if you exclude issues related to personnel, lack of skills, and personal problems.
2 | Wrong date | HoanTX | Completed | Revise the date in part 2.1 (Iteration 4 should correct this section to ensure accuracy and appropriateness).
3 | Wrong template | HoanTX | Completed | Redo the sections according to the template.
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 3: SRS v1.0 (Overall Requirement) | HoanTX | 2026-01-18 | Continue updating report 3 as previously assigned.
2 | Report 3: SRS v1.0 (Overall Requirement) | DungND | 2026-01-18 | Continue updating report 3 as previously assigned.
3 | Report 3: SRS v1.0 (Overall Requirement) | DangPH | 2026-01-18 | Continue updating report 3 as previously assigned.
4 | Report 3: SRS v1.0 (Overall Requirement) | GiangPT | 2026-01-18 | Continue updating report 3 as previously assigned.
5 | Report 3: SRS v1.0 (Overall Requirement) | HieuDM | 2026-01-18 | Continue updating report 3 as previously assigned.
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W3
PROJECT REPORT
Group | SEP490_G39
Week | 19/01/2026-25/01/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 3: SRS v1.0 (Overall Requirement) | HoanTX | Completed | Entity Relationship Diagram, Business Rules
2 | Report 3: SRS v1.0 (Overall Requirement) | DungND | Completed | Main Workflows, Actors, Context Diagram, System Messages
3 | Report 3: SRS v1.0 (Overall Requirement) | DangPH | Completed | Non-UI Functions, Non-Functional Requirements
4 | Report 3: SRS v1.0 (Overall Requirement) | GiangPT | Completed | Use Cases
5 | Report 3: SRS v1.0 (Overall Requirement) | HieuDM | Completed | Use Cases, Non-Functional Requirements, design mockup
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | The context diagram is missing an actor. | DungND | Completed | In context, actors are categorized by roles, not by department in general.
2 | Incorrect entries in the manage sections. | GiangPT | Completed | Separate the use cases into two parts: web and mobile. Separate the use case for the materials/supplies part.
3 | Erd Diagram | HoanTX | Completed | 1. Limit the number of diamonds in the middle of relationships (only text / avoid confusion) 2. Redefine the relationships 3. Clarify the entities and relationships Revise the relationships of Customer-WaterMeter, Supply-Estimation, Customer-Roadmap. Re-examine the relationship between User-WaterSupplyNetwork, rename PendingConstructionRequest 4. Understand the component measurement units
4 | Use Case diagram | GiangPT | Completed | 1. Missing system name 2. Misuse of the word "manage" to describe use cases 3. Searching and filtering bills are simple operations belonging to the view use case, not considered use cases 4. Not clustering use cases into tabs 5. Use cases that could be used extend from "manage"
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 3: SRS v1.0 (Overall Requirement) | HoanTX | 2026-01-25 | Continue updating report 3 as previously assigned.
2 | Report 3: SRS v1.0 (Overall Requirement) | DungND | 2026-01-25 | Continue updating report 3 as previously assigned.
3 | Report 3: SRS v1.0 (Overall Requirement) | DangPH | 2026-01-25 | Continue updating report 3 as previously assigned.
4 | Report 3: SRS v1.0 (Overall Requirement) | GiangPT | 2026-01-25 | Continue updating report 3 as previously assigned.
5 | Report 3: SRS v1.0 (Overall Requirement) | HieuDM | 2026-01-25 | Continue updating report 3 as previously assigned.
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W4
PROJECT REPORT
Group | SEP490_G39
Week | 26/01/2026-01/02/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 3: SRS v1.0 (Overall Requirement) | HoanTX | Completed | Update use case diagram, Update main workflows, Update ERD Diagram
2 | Report 3: SRS v1.0 (Overall Requirement) | DungND | Completed | Update the context diagram and actor list, and start writing the use case specification.
3 | Report 3: SRS v1.0 (Overall Requirement) | DangPH | Completed | Update ERD Diagram, Update use case list, Update use case diagram
4 | Report 3: SRS v1.0 (Overall Requirement) | GiangPT | Completed | Update ERD Diagram, Update use case diagram
5 | Report 3: SRS v1.0 (Overall Requirement) | HieuDM | Completed | Update screen flow, Update use case list, screen authorization.
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Incorrect cost and time estimates | HoanTX | Completed | Rewrite it as a list of use cases.
2 | AI problems. | DangPH | Completed | Learn more about AI problems.
3 | Feedback from the lecturer | All team | Completed | - Issues related to accuracy and cost, data storage problems - Show the entire process of researching the price and cost of renting external servers - Calculate long-term solutions for the cost of external call and reuse services - Determine if the server can handle the load if many people access it at the end of the month - Request and response for inventory
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 3: SRS v1.0, Report 4: SDS v1.0 | HoanTX | 2026-02-01 | Update the shortcomings in reports 1, 2, and 3 and implement report 4.
2 | Report 3: SRS v1.0, Report 4: SDS v1.0 | DungND | 2026-02-01 | Update the shortcomings in reports 1, 2, and 3 and implement report 4.
3 | Report 3: SRS v1.0, Report 4: SDS v1.0 | DangPH | 2026-02-01 | Update the shortcomings in reports 1, 2, and 3 and implement report 4.
4 | Report 3: SRS v1.0, Report 4: SDS v1.0 | GiangPT | 2026-02-01 | Update the shortcomings in reports 1, 2, and 3 and implement report 4.
5 | Report 3: SRS v1.0, Report 4: SDS v1.0 | HieuDM | 2026-02-01 | Update the shortcomings in reports 1, 2, and 3 and implement report 4.
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W5
PROJECT REPORT
Group | SEP490_G39
Week | 02/01/2026-08/02/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 3: SRS v1.0 (Overall Requirement) | HoanTX | Completed | Update use case diagram, Update main workflows, Update ERD Diagram
2 | Report 3: SRS v1.0 (Overall Requirement) | DungND | Completed | Update the context diagram and actor list, and start writing the use case specification.
3 | Report 3: SRS v1.0 (Overall Requirement) | DangPH | Completed | Update ERD Diagram, Update use case list, Update use case diagram
4 | Report 3: SRS v1.0 (Overall Requirement) | GiangPT | Completed | Update ERD Diagram, Update use case list, Update use case diagram
5 | Report 3: SRS v1.0 (Overall Requirement) | HieuDM | Completed | Update screen flow and screen authorization.
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 3: SRS v1.0, Report 4: SDS v1.0 | HoanTX | 2026-02-08 | Update the shortcomings in reports 1, 2, and 3 and implement report 4.
2 | Report 3: SRS v1.0, Report 4: SDS v1.0 | DungND | 2026-02-08 | Update the shortcomings in reports 1, 2, and 3 and implement report 4.
3 | Report 3: SRS v1.0, Report 4: SDS v1.0 | DangPH | 2026-02-08 | Update the shortcomings in reports 1, 2, and 3 and implement report 4.
4 | Report 3: SRS v1.0, Report 4: SDS v1.0 | GiangPT | 2026-02-08 | Update the shortcomings in reports 1, 2, and 3 and implement report 4.
5 | Report 3: SRS v1.0, Report 4: SDS v1.0 | HieuDM | 2026-02-08 | Update the shortcomings in reports 1, 2, and 3 and implement report 4.
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W6
PROJECT REPORT
Group | SEP490_G39
Week | 23/02/2026-01/03/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 4: SDS v1.0 | HoanTX | Completed | Package Diagram
2 | Report 3: SRS v1.0 (Overall Requirement) | DungND | Completed | Use case specification, Functional Requirements
3 | Report 4: SDS v1.0 | DangPH | Completed | Software Architecture
4 | Report 4: SDS v1.0 | GiangPT | Completed | Database Design
5 | Report 4: SDS v1.0 | HieuDM | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 4: SDS v1.0 | HoanTX | 2026-03-01 | Draw a sequence diagram,
2 | Report 3: SRS v1.0 + Report 5. Test | DungND | 2026-03-01 | Write runctional requirements, use case specifications, and integration tests.
3 | Learn about | DangPH | 2026-03-01 | Learn about AI, operating costs, deployment, and server leasing.
4 | Report 5: Test | GiangPT | 2026-03-01 | Write unit tests and integration tests.
5 | Report 4: SDS + Report 5: Test | HieuDM | 2026-03-01 | Write unit tests and integration tests + Draw a sequence diagram
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W7
PROJECT REPORT
Group | SEP490_G39
Week | 02/03/2026-08/03/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 4: SDS v1.0 | HoanTX | Completed | Draw a sequence diagram,
2 | Report 3: SRS v1.0 + Report 5. Test | DungND | Completed | Write runctional requirements, use case specifications, and integration tests.
3 | Learn about | DangPH | Completed | Learn about AI, operating costs, deployment, and server leasing.
4 | Report 5: Test | GiangPT | Completed | Write unit tests and integration tests + system test.
5 | Report 4: SDS + Report 5: Test | HieuDM | Completed | Write unit tests and integration tests + Draw a sequence diagram
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 4: SDS v1.0 | HoanTX | 2026-03-08 | Draw a sequence diagram,
2 | Report 3: SRS v1.0 + Report 5. Test | DungND | 2026-03-08 | Write runctional requirements, use case specifications, and integration tests.
3 | Learn about | DangPH | 2026-03-08 | Learn about AI, operating costs, deployment, and server leasing.
4 | Report 5: Test | GiangPT | 2026-03-08 | Write unit tests and integration tests + system test.
5 | Report 4: SDS + Report 5: Test | HieuDM | 2026-03-08 | Write unit tests and integration tests + Draw a sequence diagram
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W8
PROJECT REPORT
Group | SEP490_G39
Week | 09/03/2026-15/03/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 4: SDS v1.2 | HoanTX | Completed | Sequence diagram, Class diagram
2 | Report 3: SRS v1.2 | DungND | Completed | Use case specification, Functional Requirements
3 | AI | DangPH | Completed | Reporting, AI Training, and Improving AI Reliability
4 | Report 5: Testing | GiangPT | Completed | Unit Test, Integration Test
5 | Report 4: SDS v1.2 | HieuDM | Completed | Sequence diagram, Class diagram
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 4: SDS v1.2 | HoanTX | 2026-03-15 | Sequence diagram, Class diagram
2 | Report 3: SRS v1.2 | DungND | 2026-03-15 | Use case specification, Functional Requirements
3 | AI | DangPH | 2026-03-15 | Reporting, AI Training, and Improving AI Reliability
4 | Report 5: Testing | GiangPT | 2026-03-15 | Unit Test, Integration Test
5 | Report 4: SDS v1.2 | HieuDM | 2026-03-15 | Sequence diagram, Class diagram
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W9
PROJECT REPORT
Group | SEP490_G39
Week | 16/03/2026-22/03/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 4: SDS v1.2 | HoanTX | Completed | Sequence diagram, Class diagram
2 | Report 3: SRS v1.2 | DungND | Completed | Use case specification, Functional Requirements
3 | AI | DangPH | Completed | Reporting, AI Training, and Improving AI Reliability
4 | Report 5: Testing | GiangPT | Completed | Unit Test, Integration Test
5 | Report 4: SDS v1.2 | HieuDM | Completed | Sequence diagram, Class diagram
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 4: SDS v1.2 | HoanTX | 2026-03-22 | Sequence diagram, Class diagram
2 | Report 3: SRS v1.2 | DungND | 2026-03-22 | Use case specification, Functional Requirements
3 | AI | DangPH | 2026-03-22 | Reporting, AI Training, and Improving AI Reliability
4 | Report 5: Testing | GiangPT | 2026-03-22 | Unit Test, Integration Test
5 | Report 4: SDS v1.2 | HieuDM | 2026-03-22 | Sequence diagram, Class diagram
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W10
PROJECT REPORT
Group | SEP490_G39
Week | 23/03/2026-29/03/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 4: SDS v1.2 | HoanTX | Completed | Sequence diagram, Class diagram
2 | Report 3: SRS v1.2 | DungND | Completed | Use case specification, Functional Requirements
3 | AI | DangPH | Completed | Reporting, AI Training, and Improving AI Reliability
4 | Report 5: Testing | GiangPT | Completed | Unit Test, Integration Test
5 | Report 4: SDS v1.2 | HieuDM | Completed | Sequence diagram, Class diagram
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 4: SDS v1.2 + Report 6 SoftwareUserGuides | HoanTX | 2026-03-29 | Sequence diagram, Class diagram, Deliverable Package, Installation Guides
2 | Report 3: SRS v1.2 + Report 6 SoftwareUserGuides | DungND | 2026-03-29 | Use case specification, Functional Requirements, User Manual
3 | AI | DangPH | 2026-03-29 | Reporting, AI Training, and Improving AI Reliability
4 | Report 5: Testing | GiangPT | 2026-03-29 | Unit Test, Integration Test
5 | Report 4: SDS v1.2 | HieuDM | 2026-03-29 | Sequence diagram, Class diagram
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W11
PROJECT REPORT
Group | SEP490_G39
Week | 30/03/2026-05/04/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 4: SDS v1.2 + Report 6 SoftwareUserGuides | HoanTX | Completed | Sequence diagram, Class diagram, Deliverable Package, Installation Guides
2 | Report 3: SRS v1.2 + Report 6 SoftwareUserGuides | DungND | Completed | Use case specification, Functional Requirements, User Manual
3 | AI | DangPH | Completed | Reporting, AI Training, and Improving AI Reliability
4 | Report 5: Testing | GiangPT | Completed | Unit Test, Integration Test, System Test
5 | Report 4: SDS v1.2 | HieuDM | Completed | Sequence diagram, Class diagram, Class Specifications
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 4: SDS v1.2 + Report 7 Final Project Report | HoanTX | 2026-04-05 | Sequence diagram, Class diagram, Write Report 7 and revise the other reports
2 | Report 3: SRS v1.2 + Report 7 Final Project Report | DungND | 2026-04-05 | Use case specification, Functional Requirements, Write Report 7 and revise the other reports
3 | Report 4: SDS | DangPH | 2026-04-05 | Sequence diagram, Class diagram, Class Specifications
4 | Report 5: Testing | GiangPT | 2026-04-05 | Unit Test, Integration Test, System Test
5 | Report 4: SDS v1.2 + Slide | HieuDM | 2026-04-05 | Sequence diagram, Class diagram, Class Specifications
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W12
PROJECT REPORT
Group | SEP490_G39
Week | 06/04/2026-12/04/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 4: SDS v1.2 + Report 7 Final Project Report | HoanTX | Completed | Sequence diagram, Class diagram, Write Report 7 and revise the other reports
2 | Report 3: SRS v1.2 + Report 7 Final Project Report | DungND | Completed | Use case specification, Functional Requirements, Write Report 7 and revise the other reports
3 | Report 4: SDS | DangPH | Completed | Sequence diagram, Class diagram, Class Specifications
4 | Report 5: Testing | GiangPT | Completed | Unit Test, Integration Test, System Test
5 | Report 4: SDS v1.2 + Slide | HieuDM | Completed | Sequence diagram, Class diagram, Class Specifications
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 4: SDS v1.2 + Report 7 Final Project Report | HoanTX | 2026-04-12 | Sequence diagram, Class diagram, Write Report 7 and revise the other reports
2 | Report 3: SRS v1.2 + Report 7 Final Project Report | DungND | 2026-04-12 | Use case specification, Functional Requirements, Write Report 7 and revise the other reports
3 | Report 4: SDS | DangPH | 2026-04-12 | Sequence diagram, Class diagram, Class Specifications
4 | Report 5: Testing | GiangPT | 2026-04-12 | Unit Test, Integration Test, System Test
5 | Report 4: SDS v1.2 + Slide | HieuDM | 2026-04-12 | Sequence diagram, Class diagram, Class Specifications
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W13
PROJECT REPORT
Group | SEP490_G39
Week | 12/04/2026-18/04/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Report 4: SDS v1.2 + Report 7 Final Project Report | HoanTX | Completed | Sequence diagram, Class diagram, Write Report 7 and revise the other reports
2 | Report 3: SRS v1.2 + Report 7 Final Project Report | DungND | Completed | Use case specification, Functional Requirements, Write Report 7 and revise the other reports
3 | Report 4: SDS | DangPH | Completed | Sequence diagram, Class diagram, Class Specifications
4 | Report 5: Testing | GiangPT | Completed | Unit Test, Integration Test, System Test
5 | Report 4: SDS v1.2 + Slide | HieuDM | Completed | Sequence diagram, Class diagram, Class Specifications
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 4: SDS v1.2 + Report 7 Final Project Report | HoanTX | 2026-04-18 | Sequence diagram, Class diagram, Write Report 7 and revise the other reports
2 | Report 7 Final Project Report | DungND | 2026-04-18 | Use case specification, Functional Requirements, Write Report 7 and revise the other reports
3 | Report 4: SDS | DangPH | 2026-04-18 | Sequence diagram, Class diagram, Class Specifications
4 | Report 5: Testing | GiangPT | 2026-04-18 | Unit Test, Integration Test, System Test
5 | Report 4: SDS v1.2 + Slide | HieuDM | 2026-04-18 | Sequence diagram, Class diagram, Class Specifications
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes

## W14
PROJECT REPORT
Group | SEP490_G39
Week | 19/04/2026-26/04/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | All report + Slide | HoanTX | Completed | Complete and edit reports and design presentation slides.
2 | All report + Slide | DungND | Completed | Complete and edit reports and design presentation slides.
3 | All report + Slide | DangPH | Completed | Complete and edit reports and design presentation slides.
4 | All report + Slide | GiangPT | Completed | Complete and edit reports and design presentation slides.
5 | All report + Slide | HieuDM | Completed | Complete and edit reports and design presentation slides.
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1
2
3
4
5
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes